## E3-MV
(F120-PTB ZONE A) CAS E1 Electrical Services. HV, MV Switchgear & RMU's Commissioning Activity Schedule
Item No. | Engineers Reference | Asset Code |  |  |  | Location | Fed From | Provides Power to | Substation | Power On Date | Panel Testing | [10 empty] | Consultant Accepted | Test Sheets Filed | 13.8kV MV Cable Test |  |  | Consultant Accepted | Test Sheets Filed | Comments | Action By | Action Date
|  | Building / Zone | Category | Floor Level | Seq. No. | [5 empty] | Torque Test | IR Test | Hi Pot Test | VT Test | CT Test | Primary Injection | Secondary Injection | Ductor Test | Functional test | Protective Relay Final Settings | Site Panel Test Progress |  |  | Cable IR and Hi Pot | Consultant Accepted | Test Sheets Filed
MV Switchgears
1 | MVS (TR-A1-01) | F120 - A1 | MVS | 000 | 1 | Room MV-A1-A | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A1-01
2 | MVS (TR-A1-02) | F120 - A1 | MVS | 000 | 2 | Room MV-A1-B | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A1-02
3 | MVS (TR-HVAC-A1-01) | F120 - A1 | MVS | 000 | 3 | Room MV-A1-A | F-C13 FEEDER "B", F-C13 FEEDER "A" | TR-HVAC-A1-01
4 | MVS (TR-HVAC-A1-02) | F120 - A1 | MVS | 000 | 4 | Room MV-A1-B | F-C13 FEEDER "B", F-C13 FEEDER "A" | TR-HVAC-A1-02
5 | MVS (TR-A2-01) | F120 - A2 | MVS | 000 | 1 | Room MV-A2-A | F-C13 FEEDER "B", F-C13 FEEDER "A" | TR-A2-01
6 | MVS (TR-A2-02) | F120 - A2 | MVS | 000 | 2 | Room MV-A2-B | F-C13 FEEDER "B", F-C13 FEEDER "A" | TR-A2-02
7 | MVS (TR-A3-01) | F120 - A3 | MVS | 000 | 1 | Room MV-A3-A | F-C12 FEEDER "B", F-C12 FEEDER "A" | TR-A3-01
8 | MVS (TR-A3-02) | F120 - A3 | MVS | 000 | 2 | Room MV-A3-B | F-C12 FEEDER "B", F-C12 FEEDER "A" | TR-A3-02
9 | MVS (TR-A4-01) | F120 - A4 | MVS | 000 | 1 | Room MV-A4-A | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A4-01
10 | MVS (TR-A4-02) | F120 - A4 | MVS | 000 | 2 | Room MV-A4-B | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A4-02
11 | MVS (TR-A4-01) | F120 -A4 | MVS | 000 | 3 | Room MV-A4-A | F-C15 FEEDER "B", F-C15 FEEDER "A" | TR-A4-01
12 | MVS (TR-A4-02) | F120 -A4 | MVS | 000 | 4 | Room MV-A4-B | F-C15 FEEDER "B", F-C15 FEEDER "A" | TR-A4-02
13 | MVS (TR-A5-01) | F120 - A5 | MVS | 000 | 1 | Room MV-A5-A | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A5-01
14 | MVS (TR-A5-02) | F120 - A5 | MVS | 000 | 2 | Room MV-A5-B | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A5-02
15 | MVS (TR-A6-01) | F120 - A6 | MVS | 000 | 1 | Room MV-A6-A | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A6-01
16 | MVS (TR-A6-02) | F120 - A6 | MVS | 000 | 2 | Room MV-A6-B | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A6-02
17 | MVS (TR-A7-01) | F120 - A7 | MVS | 000 | 1 | Room MV-A7-A | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A7-01
18 | MVS (TR-A7-02) | F120 - A7 | MVS | 000 | 2 | Room MV-A7-B | F-C14 FEEDER "B", F-C14 FEEDER "A" | TR-A7-02
Summary of HV, MV Switchgear & RMU's Commissioning and Testing
[7 empty] | EQUIPMENT |  | Panel & Cable Test Progress |  |  |  |  | Overall
| Master System |  | Category Code | [5 empty] | QTY | Panel |  | Cable |  |  | Weighting: 90% Panel + 10% Cable
| HV Switchgear |  | HVS |  |  |  | HV Switchgear |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0!
| MV Switchgear |  | MVS |  |  |  | MV Switchgear |  | 18 | 0% |  | 0% |  | 0%
[7 empty] | Totals |  | N/A | #DIV/0! |  | #DIV/0! |  | #DIV/0!
#DIV/0!